# Project Planning Phase

# Planning Template(Product Backlog, Sprint Planning, Stories, Story Points)

| Date | 03 November 2025 |
| --- | --- |
| Team Id | NM2025TMID02009 |
| Project Name | Streamlining ticket assignment for efficient support operations |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule and Estimation:

Product Backlog:

| ID | User Story / Feature | Priority | Description |
| --- | --- | --- | --- |
| PB1 | As an admin, I want to define assignment rules | High | Create business rules in ServiceNow to automate ticket assignment. |
| PB2 | As a support manager, I want to configure skill-based routing | High | Enable assignment based on agent skills and expertise. |
| PB3 | As a user, I want tickets to be assigned instantly | Medium | Implement automated routing workflow using Flow Designer. |
| PB4 | As a manager, I want to monitor real-time ticket status | Medium | Build dashboards to track open, assigned, and resolved tickets. |
| PB5 | As an admin, I want performance analytics for tracking efficiency | Medium | Integrate Performance Analytics to measure KPIs like response time. |
| PB6 | As a user, I want notifications when tickets are updated | Low | Configure automated email/SMS notifications for ticket actions. |

Sprint Schedule:

| Sprint No. | Duration | Sprint Goal | Major Tasks |
| --- | --- | --- | --- |
| Sprint 1 | Week 1–2 | Requirement gathering and workflow design | Collect process requirements, map ticket flow, define business rules. |
| Sprint 2 | Week 3–4 | Develop and configure automated assignment workflow | Build assignment rules, configure Flow Designer, test routing logic. |
| Sprint 3 | Week 5–6 | Dashboard and performance analytics setup | Create dashboards, configure KPIs, monitor ticket efficiency. |
| Sprint 4 | Week 7–8 | Testing and optimization | Conduct functional and performance testing, fix workflow issues. |
| Sprint 5 | Week 9 | Documentation and final deployment | Prepare documentation, present results, deploy final system. |

Estimation:

| Task / Feature | Estimated Effort (Hours) | Assigned To (Role) | Dependencies |
| --- | --- | --- | --- |
| Requirement gathering | 8 | Business Analyst | None |
| Workflow design | 10 | Developer | Requirement completion |
| Assignment rule configuration | 12 | Developer | Workflow design |
| Skill-based routing setup | 10 | Developer | Assignment rules |
| Dashboard creation | 8 | Developer / Analyst | Workflow completion |
| Notification setup | 6 | Developer | Dashboard integration |
| Testing & debugging | 14 | Tester | All features complete |
| Performance analysis | 8 | Tester / Analyst | Testing results |
| Final deployment & documentation | 6 | Project Lead | Approval & testing |

Summary:

This Agile-based plan ensures a structured and iterative development process for implementing the ServiceNow automation system. Each sprint delivers a functional component, and the estimation ensures realistic time allocation for smooth execution.